## Group member 1
To-do list
To be completed by: |  |  |  | Name: Mohab, Ilya, Ranjan, Gabriel, Ismail
Deadline: |  | 2025-11-30 |  | Date 11/30
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Research | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-11-23
100% | Divide Work | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24
100% | Create Schemas/UDTS | 2025-11-24 | 2025-11-28 | 2025-11-28 | 2025-11-30 | Needed new tables and data provided by other peoples table
100% | Work on Reference | 2025-11-25 | 2025-11-28 | 2025-11-30 | 2025-11-30 | Fix data integration from other tables
100% | Work on Inventory | 2025-11-26 | 2025-11-28 | 2025-11-28 | 2025-11-30 | Worked on normalizing other tables
100% | Work on Sales | 2025-11-27 | 2025-11-28 | 2025-11-28 | 2025-11-30
100% | Inline Functions | 2025-11-27 | 2025-11-28 | 2025-11-28 | 2025-11-30
100% | Create ERD | 2025-11-28 | 2025-11-30 | 2025-11-30 | 2025-11-30 | Needed fully complete tables to finish this
100% | Powerpoint and Video | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2025-11-30

## Group member 2
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 3
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 4
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 5
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 6
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up